## Slide 1
https://www.officetimeline.com/14-days-trial

## Slide 2
Research
Organizational
Development
Operations
Q2
Q3
Q4
100%
Goals & Objectives
100%
Preliminary Approval
100%
Sector Investment Opportunities Research
100%
Prepare Summary Report
100%
Obtain Go/No Go Approval
100%
Organizational Development Plan
100%
Search & Hire Director
80%
Establish Budget & Get Approval
Hire First Staff Member
Staff Training
100%
Sector Investment Plan
20%
Hire Second Staff Member
Conduct Second Staff Training
Update Sector Investment Plan
Sector Investment Research
Investment Review
Make Initial Investments
Performance Review
Q1
Present Summary Report
Begin Operations
Decision to Continue/Terminate
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
Jan
Feb
Mar
Investment organization build-out plan
Risk Status
High
Medium
Low
Key Risks:
1. Org. changes at CFO level
2. Delays in team hiring plan
Potential Recovery Points:
1. Shorten training time
2. Accelerate completion of sector investment plan
Project two- month delay
CFO Change Delays Decision
Made with

## Slide 3
2022
2023
Pre-planning
Detail-planning
Gather support
Execution
2022
2023
Review Financial History and Funding Requirements Plans
100%
Review other Operations, Marketing, Personnel, and Facilities Plans for Consistency
100%
Determine Funds Needs and Timeframe
100%
100%
Review and Coordinate with Senior Management
100%
Build Presentation for Board of Directors
100%
Post Board of Director's Meeting Guidance Implementation
Create Requirements Package for Financial Consultant
Select and Orient Financial Consultant
Create IPO Detailed Plan
Investigate Commercial Sources
Conduct Interviews
Negotiate Contract, Conduct Kick Off Meeting
Review Financial Preparations for Start of IPO
Filings
Regulatory Q&A
Promotional Materials
Media Presentations
Present to Board of Directors
Go/No Go Decision
Review Number 1
Review Number 2
Obtain Approval to Proceed with IPO
Review Number 3
IPO Start Date
First Day of Public Trading
Research Coverage Begins
Issue First Earnings Forecast
Jan
Mar
May
Jul
Sep
Nov
Jan
Mar
May
Jul
Today
18 days
Apr 1 - Apr 26
18 days
Apr 8 - May 3
18 days
Apr 22 - May 17
3 days
May 20 - May 24
3 days
May 27 - May 31
Jun 3
3 days
Jun 3 - Jun 7
Jun 10
18 days
Jun 10 - Jul 5
13 days
Jul 8 - Jul 26
8 days
Jul 29 - Aug 9
Aug 9
18 days
Aug 12 - Sep 6
18 days
Sep 9 - Oct 4
8 days
Oct 7 - Oct 18
3 days
Oct 21 - Oct 25
Oct 25
18 days
Oct 28 - Nov 22
18 days
Nov 25 - Dec 20
Dec 20
Dec 23
28 days
Nov 4 - Dec 13
0 days
Dec 24 - Dec 25
Dec 25
Feb 20
Apr 17
Apr 17
First Quiet Period
Second Quiet Period
Media cover begins, but release of earnings forecast is restricted.
IPO Schedule Timeline
Resources
Board of Directors
Consultant
Finance Department
Government
Purchasing Department
Senior Management
Made with

## Slide 4
Vortex
Uno Wear
Swish Wallet
Allure Kit
ONEset
Towlee
InstaPress
Villafy
Mono
Sharpy Knife
Rhino Case
Onovo Supply
2019
2020
2021
2022
2023
2024
2025
2026
2027
2028
2029
2030
Series A - $84MM
B - $38MM
C - $84MM
Series A - $22MM
B - $11MM
Series A - $32MM
B - $31MM
C - $30MM
D - $75MM
E - $19MM
Series A - $13MM
Series A - $66MM
B - $75MM
Series A - $18MM
B - $82MM
C - $67MM
Series A - $84MM
B - $50MM
Series A - $12MM
Series A - $10MM
B - $43MM
C - $30MM
D - $43MM
Series A - $17MM
B - $18MM
Series A - $58MM
Series A - $80MM
B - $52MM
$220MM Acquisition
Liquidation
$400MM Acquisition
$300MM Acquisition
$600MM IPO
$2.5B IPO
Liquidation
Venture Capital Timeline
Key Events
Acquisition
Bankruptcy
Follow-on Investor
IPO
Lead Investor
No Participation
Made with

## Slide 5
Regional Expansion
Program Planning
Program Overview
Today
2020
2021
2022
West Region
65%
East Region
70%
North Region
80%
South Region
75%
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
Review of previous expansion
Consolidate lessons learned
Draft guidance
Internal review
Finalize guidance
Guidance approval
Official Program Launch
Assemble market research teams
Planning guidance
Consolidate research results
5-year plan approval
Preliminary market analysis
Regional projections
Regional budgeting
Planning
5-year expansion program preliminary execution
70%
Expansion teams
Regional market research
Regional expansion targets
Prioritize locations
Regional Branch Bank Expansion Program Schedule
Made with
Resources
Corporate
Consultants
Antitrust litigation
Land acquisition delays