## Slide 1
The Office Timeline add-in for PowerPoint will help you edit it with just a few clicks.
Get your free 14-day trial of Office Timeline here: https://www.officetimeline.com/14-days-trial Re-open this template, and create your impressive PowerPoint visual in 3 easy steps:
How to update this template in seconds
1
2
3
Click the Edit Data button on the Office Timeline tab.
Use the Data and Timeline views to edit swimlanes, milestones and tasks.
Click Save to instantly update the template.

## Slide 2
Phase I
Phase II
Phase III
2022
2023
18 mons
Jan 2022 - Jun 2023
Trial
Jul 2023 - Feb 2025
19 mons
Trial
13 mons
Sep 2024 - Oct 2025
Trial
Jan
May
Sep
Jan
May
Sep
Jan
May
Sep
Jan
May
Sep
2024
2025
Report
Oct 15 '22
Apply for Drug Approval
Aug 10 '24
Report
May 18 '25
Estimated Drug Approval Date
Nov 11 '25
Patients Recruited
Feb 4 '22
Patients
Enrolled
Jun 3 '22
Study Kick-off
Sep 9 '22
Patients
Recruited
Aug 3 '23
Patients
Enrolled
Dec 7 '23
Study
Kick-off
Apr 4 '24
Study
Modified
Jul 13 '24
Patients
Recruited
Oct 7 '24
Patients
Enrolled
Jan 31 '25
Study
Kick-off
May 8 '25
Made with
Stages
Recruitment
Enrollment
Kick-off
Modifications
Clinical Trial Gantt chart

## Slide 3
MDR
IVDD
IVDR
MDD
2017
2018
2019
2020
2021
2022
2023
2024
2025
May 2020 - May 2024
Certificates issued under MDD before MDR fully applies valid for up to 4 years
May 2024 - Jun 2025
MDD devices on market continue to be made available
May 2017 - May 2020
Certificates under Medical Device Directive (MDD) are valid
May 2017 - May 2024
Devices in conformity with the Medical Device Regulation (MDR) can be certified under the MDR and placed on the market
May 2024 - Dec 2025
Devices placed on market must be certified under MDR
May 2017 - May 2022
Certificates issued under In Vitro Diagnostic Medical Device Regulation (IVDR) are valid
May 2022 - May 2024
Certificates issued under IVDD before IVDR fully applies valid for up to 2 years
May 2024 - May 2025
IVDR devices on market can continue to be made available
May 2017 - May 2024
Devices in conformity with the In Vitro Diagnostic Medical Device Regulation (IVDR) can be certified under the IVDR and placed on the market
May 2024 - Dec 2025
Devices placed on market must be certified under IVDR
Regulations Enacted
May 26, 2017
MDR Fully Applies
May 26, 2020
IVDR Fully Applies
May 26, 2022
Made with
EU Regulations for MDR and IVDR
Medicines & Healthcare Regulatory Agency CE Certificates Timeline

## Slide 4
Lifecycle
Selection
Reviews
Today
2018
2024
2030
2036
2042
2048
2054
2060
2066
4.5 years
Discovery
5.5 years
Pre-clinical
26.5 years
Clinical Trials
12.5 years
Licensing Approval
2.5 years
Availability
2018 - 2022
10K Candidates
2022 - 2028
20 Candidates
2028 - 2035
10 Candidates
2035 - 2043
2-5 Candidates
2043 - 2054
1-2 Drug Candidates
2054 - 2067
1 Drug
Phase 1 Review
Dec 2034
Phase 2 Review
Jul 2043
Phase 3 Review
Jul 2054
Approval
Jan 2067
NDA Submission
Dec 2027
IND Submission
Jul 2022
Drug Selection
Feb 2019
Made with
Pharmaceutical Product Discovery
Timeline for drug discovery, industry average.

## Slide 5
Product Alpha
Product Beta
Product Gamma
Product Delta
2022
2023
Timeline
Timeline
Timeline
Timeline
Jan
Mar
May
Jul
Sep
Nov
Jan
Mar
United States
Jan 20
China
Apr 28
Japan
Jul 4
Germany
Aug 15
United Kingdom
Sep 28
India
Dec 8
United States
Mar 1
China
May 14
Japan
Jul 1
Germany
Aug 12
India
Dec 5
United Kingdom
Jan 15
United States
Apr 1
China
May 8
Japan
Jul 13
Germany
Sep 11
United Kingdom
Oct 21
India
Nov 30
United States
Apr 1
China
Jun 22
Japan
Aug 17
Germany
Nov 3
United Kingdom
Dec 30
India
Mar 1
Made with
International Pharma product launch timeline